Holy Trinity Primary

Eco Action Plan

| Implementation process (Actions to be taken) | Personnel Responsible | Time Scale (Specific Start/end dates | Resource implications (including staff development) | Success Criteria |
| --- | --- | --- | --- | --- |
| Autumn Generate ideas from school on how school grounds/ eco/ recycling could be improved around our school. Complete a formal environmental review (silver criteria) Urban Crew to create a new Eco poster – post this around school Find a parent/governor who can be a representative for the Eco Action team (Silver criteria) Discuss with LH and PL Urban Crew to make links with the local community and work with Edward Grant Court. | KG but to be carried out by Urban Crew KG and Urban Crew Urban Crew (via KG) KG KG | 8.11.13 22.11.13 20.12.13 20.12.13 TBC | Time Time Time (including contact time with children in Urban Crew) Time Time | A mind map will be created from all the ideas from school council and given to urban crew. An action plan to be then organised for these to be implemented. (silver criteria) A formal review will be created A new eco poster is to be created and then posted around school. A parent/ governor will be appointed as part of the Eco Action team to work along the subject leader KG and the Urban Crew. They must be willing to attend meetings. Urban Crew to create a visit including a litter pick to the local OAP home. (community links) |
| Spring Get PL to set up a designated Urban Crew page on the school website. To be updated with the Urban Crew actions and events. Plan a wildlife area to be placed in the school grounds. (large scale project) Carry out vegetable competition for Urban Crew - | KG PL KG- LH- Pip KG | 10.1.13 4.4.13 TBC | Time Time - Money for plants- support for planting Time | Urban Crew/ Eco will have a designated page where all the information can be placed following all the targets towards one large scale and two smaller projects. A wildlife area will be planned – discussions will be held over what resources we will need, where it will be placed and how we will plant them. Vegetables will be grown for vegetable competition. |
| Summer Urban Crew carry out a follow up visit to local OAP home- carry out a litter pick/ flower planting. Organise the resources for the wildlife area. (see free tree websites – contact eco contacts for support – also possibly MCA for guidance) If successful in getting resources for the wildlife area organise a planting session where we can invite parents and local residents in to help the children plant the new wildlife area. | KG KG- LH- Pip- Parent support KG- LH- Pip- Parent support | TBC 22.5.13 TBC | Time Time, Plants, Planting costs Time, Plants, Planting costs | Urban crew develop community cohesion by carrying out a litter pick and flower planting session at local OAP home – Edward Grant Court. Organise the resources to be collected for the wildlife area. Order these and talk with Pip in organising a summer gardening session to plant all the trees/bushes/plants etc. If possible trees/plants/bushes arrived in time a planting session with all parents and local residents to be organised to plant the new wildlife area. |